## Dashboard
RA ¦ Operations & PMO Executive Dashboard
Synthetic portfolio project for Operations / PMO / Reporting / Data Analysis
As-of Date | 2026-09-27 |  | Data note | All records are synthetic and safe for public portfolio use.
Total Tasks |  | Completed |  | Completion Rate |  | Overdue
36 |  | 13 |  | 36.11% |  | 21
Blocked |  | Open RAID |  | Red Projects |  | Projects
5 |  | 7 |  | 6 |  | 6
Status | Count |  | Priority | Count
Not Started | 6 |  | Low | 5
In Progress | 12 |  | Medium | 11
Blocked | 5 |  | High | 14
Completed | 13 |  | Critical | 6
Project | Completion % | Overdue | Blocked | Open RAID | RAG
PMO Governance Upgrade | 50% | 3 | 0 | 1 | Red
Executive Reporting Pack | 33.33% | 4 | 0 | 1 | Red
Customer Service SLA | 16.67% | 5 | 1 | 2 | Red
Inventory Accuracy | 16.67% | 4 | 2 | 1 | Red
Warehouse Process Improvement | 16.67% | 4 | 1 | 1 | Red
Recruitment Analytics | 83.33% | 1 | 1 | 1 | Red

## Projects
Project | Sponsor | Project Manager | Start Date | Target Date | Total Tasks | Completed | Completion % | Overdue | Blocked | Open RAID | RAG
PMO Governance Upgrade | COO | Owner A | 2026-08-01 | 2026-10-15 | 6 | 3 | 50% | 3 | 0 | 1 | Red
Executive Reporting Pack | CFO | Owner B | 2026-08-04 | 2026-10-20 | 6 | 2 | 33.33% | 4 | 0 | 1 | Red
Customer Service SLA | CX Director | Owner C | 2026-08-07 | 2026-10-25 | 6 | 1 | 16.67% | 5 | 1 | 2 | Red
Inventory Accuracy | Supply Chain Director | Owner D | 2026-08-10 | 2026-10-30 | 6 | 1 | 16.67% | 4 | 2 | 1 | Red
Warehouse Process Improvement | Operations Director | Owner E | 2026-08-13 | 2026-11-04 | 6 | 1 | 16.67% | 4 | 1 | 1 | Red
Recruitment Analytics | HR Director | Owner F | 2026-08-16 | 2026-11-09 | 6 | 5 | 83.33% | 1 | 1 | 1 | Red

## Tasks
Task ID | Project | Workstream | Owner | Status | Priority | Start Date | Due Date | Completion Date | Progress % | Days Variance | Notes
T-001 | PMO Governance Upgrade | Governance | Owner A | Completed | High | 2026-08-01 | 2026-08-15 | 2026-08-16 | 100% | 1 | Synthetic portfolio data
T-002 | Executive Reporting Pack | Reporting | Owner B | In Progress | High | 2026-08-04 | 2026-08-22 |  | 50% | 36 | Synthetic portfolio data
T-003 | Customer Service SLA | Service | Owner C | In Progress | Medium | 2026-08-07 | 2026-08-29 |  | 60% | 29 | Synthetic portfolio data
T-004 | Inventory Accuracy | Inventory | Owner D | Blocked | Critical | 2026-08-10 | 2026-09-05 |  | 20% | 22 | Synthetic portfolio data
T-005 | Warehouse Process Improvement | Process | Owner E | Not Started | Medium | 2026-08-13 | 2026-09-12 |  | 0% | 15 | Synthetic portfolio data
T-006 | Recruitment Analytics | Analytics | Owner F | Completed | High | 2026-08-16 | 2026-08-30 | 2026-08-30 | 100% | 0 | Synthetic portfolio data
T-007 | PMO Governance Upgrade | Governance | Owner A | In Progress | Medium | 2026-08-19 | 2026-09-06 |  | 50% | 21 | Synthetic portfolio data
T-008 | Executive Reporting Pack | Reporting | Owner B | Completed | Low | 2026-08-22 | 2026-09-13 | 2026-09-11 | 100% | -2 | Synthetic portfolio data
T-009 | Customer Service SLA | Service | Owner C | Blocked | Critical | 2026-08-25 | 2026-09-20 |  | 55% | 7 | Synthetic portfolio data
T-010 | Inventory Accuracy | Inventory | Owner D | In Progress | High | 2026-08-28 | 2026-09-27 |  | 85% | 0 | Synthetic portfolio data
T-011 | Warehouse Process Improvement | Process | Owner E | Not Started | Medium | 2026-08-31 | 2026-09-14 |  | 0% | 13 | Synthetic portfolio data
T-012 | Recruitment Analytics | Analytics | Owner F | Completed | High | 2026-09-03 | 2026-09-21 | 2026-09-19 | 100% | -2 | Synthetic portfolio data
T-013 | PMO Governance Upgrade | Governance | Owner A | In Progress | Critical | 2026-08-01 | 2026-08-23 |  | 60% | 35 | Synthetic portfolio data
T-014 | Executive Reporting Pack | Reporting | Owner B | In Progress | Medium | 2026-08-04 | 2026-08-30 |  | 75% | 28 | Synthetic portfolio data
T-015 | Customer Service SLA | Service | Owner C | Completed | High | 2026-08-07 | 2026-09-06 | 2026-09-05 | 100% | -1 | Synthetic portfolio data
T-016 | Inventory Accuracy | Inventory | Owner D | Blocked | High | 2026-08-10 | 2026-08-24 |  | 20% | 34 | Synthetic portfolio data
T-017 | Warehouse Process Improvement | Process | Owner E | Not Started | Low | 2026-08-13 | 2026-08-31 |  | 0% | 27 | Synthetic portfolio data
T-018 | Recruitment Analytics | Analytics | Owner F | Completed | Medium | 2026-08-16 | 2026-09-07 | 2026-09-07 | 100% | 0 | Synthetic portfolio data
T-019 | PMO Governance Upgrade | Governance | Owner A | Completed | Medium | 2026-08-19 | 2026-09-14 | 2026-09-13 | 100% | -1 | Synthetic portfolio data
T-020 | Executive Reporting Pack | Reporting | Owner B | In Progress | High | 2026-08-22 | 2026-09-21 |  | 85% | 6 | Synthetic portfolio data
T-021 | Customer Service SLA | Service | Owner C | In Progress | Critical | 2026-08-25 | 2026-09-08 |  | 35% | 19 | Synthetic portfolio data
T-022 | Inventory Accuracy | Inventory | Owner D | Not Started | Low | 2026-08-28 | 2026-09-15 |  | 0% | 12 | Synthetic portfolio data
T-023 | Warehouse Process Improvement | Process | Owner E | Blocked | High | 2026-08-31 | 2026-09-22 |  | 40% | 5 | Synthetic portfolio data
T-024 | Recruitment Analytics | Analytics | Owner F | Completed | Medium | 2026-09-03 | 2026-09-29 | 2026-09-27 | 100% | -2 | Synthetic portfolio data
T-025 | PMO Governance Upgrade | Governance | Owner A | In Progress | High | 2026-08-01 | 2026-08-31 |  | 85% | 27 | Synthetic portfolio data
T-026 | Executive Reporting Pack | Reporting | Owner B | Completed | Medium | 2026-08-04 | 2026-08-18 | 2026-08-18 | 100% | 0 | Synthetic portfolio data
T-027 | Customer Service SLA | Service | Owner C | Not Started | Low | 2026-08-07 | 2026-08-25 |  | 0% | 33 | Synthetic portfolio data
T-028 | Inventory Accuracy | Inventory | Owner D | In Progress | Critical | 2026-08-10 | 2026-09-01 |  | 60% | 26 | Synthetic portfolio data
T-029 | Warehouse Process Improvement | Process | Owner E | Completed | High | 2026-08-13 | 2026-09-08 | 2026-09-09 | 100% | 1 | Synthetic portfolio data
T-030 | Recruitment Analytics | Analytics | Owner F | Blocked | High | 2026-08-16 | 2026-09-15 |  | 55% | 12 | Synthetic portfolio data
T-031 | PMO Governance Upgrade | Governance | Owner A | Completed | Medium | 2026-08-19 | 2026-09-02 | 2026-09-01 | 100% | -1 | Synthetic portfolio data
T-032 | Executive Reporting Pack | Reporting | Owner B | In Progress | High | 2026-08-22 | 2026-09-09 |  | 50% | 18 | Synthetic portfolio data
T-033 | Customer Service SLA | Service | Owner C | Not Started | Medium | 2026-08-25 | 2026-09-16 |  | 0% | 11 | Synthetic portfolio data
T-034 | Inventory Accuracy | Inventory | Owner D | Completed | High | 2026-08-28 | 2026-09-23 | 2026-09-23 | 100% | 0 | Synthetic portfolio data
T-035 | Warehouse Process Improvement | Process | Owner E | In Progress | Critical | 2026-08-31 | 2026-09-30 |  | 85% | -3 | Synthetic portfolio data
T-036 | Recruitment Analytics | Analytics | Owner F | Completed | Low | 2026-09-03 | 2026-09-17 | 2026-09-15 | 100% | -2 | Synthetic portfolio data

## RAID
RAID ID | Project | Type | Description | Owner | Impact | Probability | Status | Target Date | Mitigation / Action
R-001 | PMO Governance Upgrade | Risk | Decision approvals may delay stage gates | Owner A | High | Medium | Monitoring | 2026-10-05 | Weekly escalation review
R-002 | Executive Reporting Pack | Dependency | Source systems refresh timing | Owner B | Medium | High | Open | 2026-10-02 | Lock refresh schedule
R-003 | Customer Service SLA | Issue | SLA backlog above target | Owner C | High | High | Open | 2026-09-30 | Daily recovery queue
R-004 | Inventory Accuracy | Risk | Cycle count variance remains volatile | Owner D | High | Medium | Monitoring | 2026-10-08 | Root-cause review by SKU class
R-005 | Warehouse Process Improvement | Assumption | Shift staffing remains stable | Owner E | Medium | Medium | Monitoring | 2026-10-10 | Validate weekly roster
R-006 | Recruitment Analytics | Issue | Candidate source labels inconsistent | Owner F | Medium | High | Open | 2026-10-01 | Normalize source taxonomy
R-007 | PMO Governance Upgrade | Dependency | Steering committee calendar | Owner A | Medium | Medium | Closed | 2026-09-25 | Calendar confirmed
R-008 | Customer Service SLA | Risk | Repeat contacts increasing | Owner C | Medium | Medium | Open | 2026-10-06 | Introduce first-contact-resolution review

## Lists
Status | Priority | RAID Type | RAID Status
Not Started | Low | Risk | Open
In Progress | Medium | Assumption | Monitoring
Blocked | High | Issue | Closed
Completed | Critical | Dependency